## 18-05-2026
18-MAY, 2026 REPORT — MOJEC INTERNATIONAL LIMITED ¦ DISREP METERING PROJECT
PROJECT COMPLETION: 29.8% ¦ Contract Volume: 128,800 ¦ Installed: 38,361 ¦ Remaining: 90,439 ¦
SURVEY SUMMARY |  | SURVEY BY REGION
Total Surveyed so far | 45813 | Total Survey Done In Kano | Total Survey Done In Kano | 40036
Survey Confirm on FDM | 45738 | Total Survey Done In Katsina | Total Survey Done In Katsina | 3219
Survey yet To be Confirm | 31 | Total Survey Done In Jigawa | Total Survey Done In Jigawa | 2558
Survey Rejected on FDM | 44 | Yet To Survey in Kano | Yet To Survey in Kano | 5730
Survey done in January | 9735 | Yet To Survey in Katsina | Yet To Survey in Katsina | 453
Survey done in February | 8175 | Yet To Survey in Jigawa | Yet To Survey in Jigawa | 205
Survey done in March | 4968 | Survey done Today in Kano | Survey done Today in Kano | 335
Survey done in April | 6562 | Survey done Today in Katsina | Survey done Today in Katsina | 13
Survey done in May | 3153 | Survey done Today in Jigawa | Survey done Today in Jigawa | 3
Survey done today | 351 | Survey vs Install Gap | Survey vs Install Gap | 7452
INSTALLATION SUMMARY |  | INSTALLATION BY REGION
Total KYC Uploaded on FDM | 80061 | Total Meters Installed in Kano |  | 34659
Installation done so far | 38361 | Total Meters Installed in Katsina |  | 2166
Confirmed on FDM | 37378 | Total Meters Installed in Jigawa |  | 1536
Installation yet To be Confirm | 570 | Total Installable for Kano |  | 5342
Installation Rejected on FDM | 413 | Total Installable for Katsina |  | 1235
Installation done in January | 8148 | Total Installable for Jigawa |  | 543
Installation done in February | 3158 | Installation done today in Kano |  | 307
Installation done in March | 8136 | Installation done today in Katsina |  | 36
Installation done in April | 7367 | Installation done today in Jigawa |  | 17
Installation done in May | 3431 | Single Phase Installed today |  | 292
Installation done today | 360 | Three Phase Installed today |  | 68
SBC INSTALLATION — 18-MAY-2026 |  | FEEDER INSTALLATION — 18-MAY-2026
SBC / TEAM NAME | COUNT | FEEDER NAME |  | COUNT
STARLINE11 | 57 | 33KV RIJIYAR ZAKI |  | 66
BUNIKS TEAM 1 | 44 | 11KV KUNTAU |  | 42
APOSTLE LIMITED | 34 | 11KV Nomansland |  | 40
EMDEE | 34 | 11KV Hassan Usman Road |  | 36
BUNIKS KATSINA | 23 | 11KV NOMANSLAND |  | 29
FAB NEXUS 3 | 22 | 11KV Marhaba |  | 26
STARLINE10 | 18 | 11KV Kofar Naisa |  | 23
BORNTECH | 16 | 11KV Hausawa |  | 17
SHADATECH8 | 15 | 11KV SABON GARI |  | 9
M & I | 14 | 33KV BIRNIN KUDU |  | 9
MDALIFU KANO | 11 | 11KV Sani Abacha Way |  | 8
BINAS DUTSE3 | 9 | 11KV Hotoro |  | 7
US KEANA 3 | 9 | 11KV sabon Gari |  | 7
BINAS DUTSE2 | 8 | 11KV NNDC |  | 6
SHADATECH3 | 6 | 11KV YANKABA |  | 6
STARLINE KATSINA1 | 6 | 11KV Independence |  | 5
STARLINE4 | 6 | 33KV BUK |  | 4
STARLINE13 | 5 | 11 KV Sallari |  | 4
APOSTLE KATSINA1 | 4 | 11KV Race Course |  | 3
SHADATECH9 | 4 | 11KV Bompai |  | 2
KUMBUTECH KATSINA | 3 | 11KV AIRPORT ROAD |  | 2
SHADATECH1 | 3 | 11KV LAMBISA |  | 2
STARLINE2 | 3 | 11KV DANLADI NASIDI |  | 1
BINAS3 | 2 | 11KV Ajasa |  | 1
BOLD TECH | 2 | 11KV Badawa |  | 1
FAB NEXUS 5 | 1 | 11KV ABUJA |  | 1
SHADATECH7 | 1 | 11KV HOTORO |  | 1
|  | 11KV Yusuf Road |  | 1
|  | 11KV YUSUF ROAD |  | 1
TOTAL | 360 | TOTAL |  | 360
Prepared by: Haruna Idris ¦ Data Analyst ¦ Mojec International Limited ¦ DISREP Metering Project ¦ 18-MAY-2026